CARDIOSENTINEL

Research Execution Handbook

From Frozen Benchmark to Patient-Adaptive Foundation-to-Edge Intelligence

Purpose: This handbook is the persistent technical memory for the CardioSentinel research program. It records the research thesis, frozen decisions, phased execution plan, model candidates, experiment tiers, evaluation rules, edge-system plan, paper-reporting strategy, and the current state of execution so that the project does not drift or lose track of earlier decisions.

Version 1.0  |  7 August 2026

Research scope: transient ischemic ST-episode monitoring decision support

# 0. How to Use This Handbook

This is not a publication draft and it is not a marketing document. It is the authoritative execution map for the research. When a future implementation choice conflicts with this document, the conflict should be resolved explicitly and recorded rather than silently changing the protocol.

| Primary goal | Build and evaluate a patient-adaptive, uncertainty-aware edge/cloud ECG monitoring system for transient ischemic ST episodes. |
| --- | --- |
| Conference target | TACTiCS 2026, Intelligent Physical Systems theme; 4-5 page IEEE-style paper. |
| Submission deadline | 31 August 2026. |
| Core evidence standard | Subject-disjoint evaluation, no test tuning, exact experiment locks, reproducible corpus and code provenance, event-level and systems-level evidence. |
| Safety wording | Detection / monitoring decision support. Do not describe CardioSentinel as making a medical diagnosis. |
| Core detector | Time-series ECG ML. An LLM/SLM may summarize structured evidence, but it is not the primary detector. |

## 0.1 The one-sentence research thesis

Research thesis: A self-personalizing wearable intelligence system can continuously model an individual's ECG, detect sustained deviation from that person's stable physiological baseline, quantify uncertainty, and dynamically divide decisions between a compact edge model and a higher-capacity cloud model.

## 0.2 What makes this research more than an ECG classifier

The benchmark is frozen before final model evaluation.

The core model is causal and designed for streaming ECG rather than offline future-aware processing.

The system explicitly models patient-specific normality using short- and long-timescale memory.

Memory updates are contamination-gated so a developing event is not learned as the new normal.

Uncertainty is used operationally to decide whether the edge model should act locally or escalate.

Temporal reasoning converts noisy window predictions into sustained episode decisions.

The final system is measured as a physical edge/cloud system: latency, memory, network traffic, and outage behavior are part of the evidence.

## 0.3 Contents / project map

Research thesis and non-negotiable scientific rules.

Target architecture and the role of CNN, Transformer, SSM, foundation model, patient memory, uncertainty, and optional LLM/SLM.

Frozen benchmark and corpus state.

Detailed phase-by-phase execution roadmap.

Neural architecture selection experiments.

Advanced experiment tiers and decision rules.

Personalization, uncertainty, temporal reasoning, and edge/cloud orchestration.

Hardware-in-the-loop and systems experiments.

Statistics, ablations, robustness, and secondary validation.

Paper-result strategy: what belongs in the 4-5 page paper and what remains in the repository.

Current execution snapshot and immediate next steps.

Experiment ledger, naming conventions, risk register, and final memory capsule.

# 1. Scientific Contract and Non-Negotiable Rules

| Rule | Meaning for this project |
| --- | --- |
| Detection, not diagnosis | Use language such as transient ischemic ST-episode detection, suspected ischemic ST-T change, and monitoring decision support. Do not claim clinical diagnosis. |
| No fabricated evidence | Never invent measurements, labels, performance values, external validation, hardware results, or patient outcomes. |
| No test tuning | The sealed LTSTDB test partition is not used to choose architecture, threshold, feature, calibration, or hyperparameter decisions. |
| Subject separation | Train, validation, calibration, and test decisions must preserve subject-level separation. |
| Causal primary pipeline | No future-sample preprocessing such as filtfilt in the primary streaming pipeline. |
| Raw profile is primary | No high-pass preprocessing is enabled by default. ST-preserving filtering is a controlled optional experiment, not an assumed preprocessing step. |
| Softmax is not calibration | Confidence/routing claims require proper calibration or selective/conformal evidence. |
| Patient memory must be safe | Do not update normal memory during suspected events, low quality, high uncertainty, or known confounder states. |
| LLM is not the detector | Language models can summarize structured evidence, explain events, or support interaction; ECG detection remains numerical signal ML. |
| No unsupported novelty claims | Use targeted literature-gap language. Do not claim 'first' unless systematically supported. |
| EDB is not automatically independent | Known EDB/LTSTDB provenance overlap must be excluded or transparently described. |
| All runs are traceable | Record Git SHA, dirty state, feature/dataset hashes, split hash, model config, seed, environment, timing, thresholds, and test-access state. |

## 1.1 If the schedule becomes tight

The research should be simplified by removing optional technology, not by weakening experimental integrity. The minimum viable scientific contribution is:

A strong compact global neural baseline.

Patient-adaptive dual-timescale memory.

Contamination-safe memory updates.

Calibrated/selective uncertainty routing.

Temporal episode reasoning.

At least one credible edge-system experiment.

Important: Foundation-model distillation, a full Transformer+SSM stack, masked self-supervision, and an LLM explanation layer are optional. They are retained only if they add measurable value within the deadline.

# 2. Target CardioSentinel Architecture

The architecture is intentionally hierarchical. Different models are assigned to different temporal and functional roles rather than stacked merely because they are fashionable.

Continuous ambulatory ECG ¦ v Causal physical signal pipeline ¦ v Compact local morphology encoder [1D CNN / TCN] ¦ v Short-context sequence model [Tiny Transformer OR SSM candidate] ¦ v Window embedding z_t ¦ +---------------------------+ ¦ ¦ v v Physiology feature stream Longitudinal temporal state (ST/QRS/T/RR proxies) [preferred SSM across windows] ¦ ¦ +-------------+-------------+ ¦ v Patient dual-memory short prototype + long prototype ¦ v patient-deviation intelligence ¦ v calibrated/selective uncertainty ¦ v temporal episode state reasoning NORMAL -> WATCH -> EVENT -> RECOVERY ¦ +-------+--------+ ¦ ¦ v v local edge action cloud escalation ¦ v higher-capacity ECG teacher ¦ v structured evidence ¦ v optional SLM / LLM summary

## 2.1 Role of each ML family

| Component | Primary role | Why it belongs | What it must not be used to claim |
| --- | --- | --- | --- |
| 1D CNN / TCN | Local morphology extraction | Efficiently learns QRS/ST/T shape, slopes, local transitions, and beat morphology from raw time series. | It is not automatically patient-adaptive or temporally episode-aware. |
| Tiny Transformer | Short-window relational attention | Can model relationships among beat/patch tokens within a short ECG window. | It should not be kept merely because attention sounds advanced. |
| SSM / Mamba-style block | Long-range temporal state | Potentially efficient for long ambulatory sequences; especially attractive across successive 10 s window embeddings. | Do not claim linear-time edge advantage until measured on our implementation. |
| ECG foundation model | High-capacity pretrained teacher | Transfers broad ECG representation knowledge to a compact student through distillation. | The FM is not required to be deployed on the edge. |
| Physiology features | Inductive bias / evidence | Explicitly expose ST, QRS, T, RR, cross-lead and morphology information to the model and later explanation layer. | Current morphology_v1 proxies are not clinically validated J/ST delineation. |
| Prototype memory | Patient personalization | Represents what is stable/normal for the current patient on short and long timescales. | Do not update blindly during abnormalities. |
| Calibration / conformal | Selective trust | Turns score uncertainty into an operational accept/escalate mechanism. | Raw softmax probability is not calibrated uncertainty. |
| Temporal state machine | Operational episode control | Adds persistence, hysteresis, recovery, and interpretable alert logic. | It does not replace neural temporal representation; it governs decisions. |
| SLM / LLM | Explanation and reporting | Converts structured event evidence into readable summaries and interaction. | It is not the ischemia detector and should not manufacture clinical conclusions. |

## 2.2 Preferred SSM placement

The preferred high-value SSM experiment is not necessarily to replace the entire CNN+Transformer encoder. The strongest conceptual use is to model the trajectory of successive window embeddings over tens of seconds or minutes.

10 s ECG #1 -> short-window encoder -> z1 10 s ECG #2 -> short-window encoder -> z2 10 s ECG #3 -> short-window encoder -> z3 ... 10 s ECG #N -> short-window encoder -> zN ¦ v longitudinal SSM ¦ v learned state h_t ¦ + patient prototype distance + physiology evidence + uncertainty ¦ v episode logic

Decision principle: If CNN+SSM performs as well as CNN+Transformer+SSM with substantially fewer parameters/latency, choose the simpler model. Architecture selection is a Pareto decision, not a competition for the largest stack.

# 3. Frozen Benchmark and Data State

| Primary dataset | Long-Term ST Database (LTSTDB), 86 recordings / 80 subjects, 21-24 h ambulatory recordings, 2/3 channels, 250 Hz. |
| --- | --- |
| Secondary dataset | European ST-T Database (EDB), used only with provenance-aware overlap handling; not automatically described as fully independent. |
| Primary window | 10 seconds. |
| Stride | 5 seconds. |
| Primary target source | LTSTDB .stb annotation semantics. |
| Frozen subjects | Train 56 / validation 12 / test 12 subjects. |
| Records | Train 60 / validation 13 / test 13 records. |
| Primary metric | AUPRC. |
| Secondary metrics | AUROC, F1, sensitivity, specificity, PPV, NPV, balanced accuracy, MCC; later episode and edge-system metrics. |
| Frozen split SHA-256 | 66e25d77b6aaa25502974b4b60667b4c4b24d649bf9493666827c747a385ced7 |
| Feature corpus SHA-256 | f18785d520828cb171482926922346dda824c8868ed4b7f9be45897cd71d6eb5 |

## 3.1 Materialized corpus

| Partition | Rows | Ischemic | Background | Rate | Axis | Conduction | Quality | Boundary | Censored |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Train | 2,208,431 | 93,613 | 2,049,986 | 24,512 | 13,630 | 7,883 | 13,099 | 2,836 | 2,872 |
| Validation | 492,904 | 21,628 | 452,269 | 4,973 | 3,000 | 164 | 10,112 | 583 | 175 |
| Test | 463,035 | 20,899 | 432,905 | 5,068 | 3,058 | 10 | 350 | 581 | 164 |
| Total | 3,164,370 | - | - | - | - | - | - | 4,000 | 3,211 |

Algorithmic morphology_v1 feature validity: 3,164,305 valid windows and 65 invalid windows (99.99794588% valid). This is an implementation-level feature-validity measure, not clinical delineation accuracy.

## 3.2 Feature schemas frozen for classical baselines

| Schema | Features | SHA-256 |
| --- | --- | --- |
| signal_v1 | 22 | 25d05f8716340e0fcc9950590025e7c58dccbfe8d0e0475ccd36bd629d4c57d4 |
| morphology_v1 | 18 | 13f60be400b5b957c1eb592bbafd8206d4d2855c1aa657a058671fb8d7cab434 |
| combined_v1 | 40 | 6b1517cb6ffd5d113a385bb252a90630f75beec4da7345185e74dda0eff98a34 |

## 3.3 Known provenance warning

Ten LTSTDB recordings are known to map directly to EDB recordings, and the conservative same-EDB-subject exclusion expands to 15 EDB records. Therefore, cross-dataset analysis must use explicit provenance-aware exclusions and modest wording.

Known direct mappings: s20021/e0113 s20151/e0103 s20161/e0105 s20171/e0127 s20181/e0162 s20291/e0104 s20301/e0125 s20311/e0129 s20581/e0603 s20591/e0604 Conservative EDB exclusions: e0103 e0104 e0105 e0113 e0123 e0124 e0125 e0126 e0127 e0129 e0133 e0162 e0163 e0603 e0604

# 4. Master Phased Roadmap

The roadmap below is the top-level control plane. The following sections expand every phase into objective, method, experiments, outputs, and exit criteria.

| Phase | Status | Core question | Primary techniques | Exit evidence |
| --- | --- | --- | --- | --- |
| 0 | COMPLETE | Can the project be reproduced and governed? | Packaging, CI, tests, provenance, legacy isolation | Research-grade repo and experiment contract |
| 1 | COMPLETE | Do we understand the data and annotation semantics? | WFDB parsing, event taxonomy, provenance mapping | Validated datasets and leakage controls |
| 2 | COMPLETE | Is the ECG pipeline causal and physically correct? | Raw identity path, causal filtering contract, unit checks, SQI | Streaming-safe signal pipeline |
| 3A | COMPLETE | Can the benchmark be frozen before results? | Subject split, targets, metrics, challenge strata | Sealed Benchmark V1 |
| 3B-1 | RUNNING | How strong are simple global feature models? | B0 prior, LR, morphology LR, HGB | Frozen classical baseline locks and sealed-test results |
| 3B-2 | NEXT | What compact raw-waveform neural baseline is strongest? | CNN/TCN, CNN+Transformer, CNN+SSM | Selected Pareto-efficient global encoder |
| 4 | PLANNED | Does physiology-guided representation help? | Feature fusion, optional contrastive learning | Ablation-backed representation gain |
| 5 | CORE | Does patient adaptation reduce false alarms safely? | Short/long prototypes, gated update, rollback | Personalization and contamination evidence |
| 6 | CORE | When should the edge trust itself? | Calibration, selective risk, optional conformal | Risk-coverage and escalation policy |
| 7 | CORE | Can windows become reliable episodes? | SSM longitudinal context, state machine, confounder logic | Episode sensitivity/PPV/FA per hour/onset |
| 8 | CORE | Can this operate as an intelligent physical system? | Pi edge runtime, MQTT, quantization, outages | Latency/RAM/network/resilience evidence |
| 9 | PLANNED | Which components actually matter? | Ablations, perturbations, secondary EDB | Contribution and robustness tables |
| 10 | PLANNED | Are claims statistically defensible? | Subject bootstrap, paired analyses, error review | Final evidence package |
| 11 | PLANNED | Can the evidence fit a 4-5 page paper? | Claim compression, tables, figures, limitations | Submission-ready manuscript |
| 12 | PLANNED | Can the exact submission state be reproduced? | Tag/release, locked artifacts, final audit | Reproducibility freeze |

# 5. Phase 0 - Research Repository and Governance [COMPLETE]

| Objective | Replace the 2020 college-project structure with a reproducible research codebase. |
| --- | --- |
| Why it exists | Without governance, later gains can be contaminated by silent preprocessing, split changes, accidental test access, or non-reproducible local artifacts. |
| Technical process | Archive the legacy algorithm; package cardiosentinel; define typed configuration, CI, pytest and Ruff; require run provenance; separate non-versioned patient-derived artifacts from Git; document research scope and claim boundaries. |
| Experiments / checks | Import/package checks; unit tests; CI; clean working-tree requirement for fitting/testing; provenance capture; storage-policy tests. |
| Outputs | Modern research repository; legacy isolation; experiment contract; reproducibility foundation. |
| Exit gate | All later phases can execute without relying on legacy fixed-threshold logic. |

Do not forget: The old fixed ST-slope threshold algorithm is history only. It must never re-enter the modern core.

# 6. Phase 1 - Dataset, Annotation and Provenance Integrity [COMPLETE]

| Objective | Establish exact event semantics, source quality states, and cross-dataset provenance. |
| --- | --- |
| Why it exists | Incorrect interpretation of ST annotations is more damaging than a weak model because it invalidates every subsequent metric. |
| Technical process | Parse LTSTDB and EDB annotations into explicit typed states; distinguish ischemic episodes, rate-related events, axis shifts, conduction changes, unreadable/noise intervals, and censored/source-specific states; map known EDB/LTSTDB overlap. |
| Experiments / checks | Record/subject counts, annotation completeness, unknown-class audit, source-manifest integrity, overlap mapping and conservative same-subject exclusion. |
| Outputs | Validated annotation parsers, source manifests, provenance documentation and cross-dataset warning policy. |
| Exit gate | No unknown relevant labels; frozen interpretation rules; known overlap explicitly controlled. |

Do not forget: Do not describe overlap-clean EDB as perfectly independent unless provenance evidence supports that wording.

# 7. Phase 2 - Causal Physical ECG Pipeline [COMPLETE]

| Objective | Create a streaming-compatible physical ECG pipeline that preserves ST information. |
| --- | --- |
| Why it exists | Offline future-aware filtering can create unrealistic performance and distort the low-frequency ST segment. |
| Technical process | Use WFDB physical samples, canonical mV conversion, exact raw identity as primary profile, bounded reads, causal filtering only when explicitly configured, 10 s windows, waveform-only signal quality, physically correct derivative/spectral units. |
| Experiments / checks | Raw identity equivalence; streaming causal state equivalence; unit-conversion tests; 200/400 Hz derivative checks; spectral-bin support; short-window validation; remote bounded waveform smoke tests. |
| Outputs | Signal-processing contract and reusable causal waveform/window abstractions. |
| Exit gate | No future leakage in the primary pipeline and unit-correct signal features. |

Do not forget: Primary experiments do not use filtfilt. Any optional high-pass profile must be explicitly justified and should remain <=0.05 Hz if explored.

# 8. Phase 3A - Frozen Benchmark, Split and Metrics [COMPLETE]

| Objective | Freeze what counts as success before evaluating model performance. |
| --- | --- |
| Why it exists | A model result is only defensible if labels, subject partitions, metrics, and threshold rules were not optimized after seeing test performance. |
| Technical process | Freeze subject-disjoint LTSTDB train/validation/test split; 10 s/5 s geometry; target precedence; challenge context; AUPRC primary metric; subject-macro and bootstrap policy; validation-only threshold selection; sealed test flag. |
| Experiments / checks | Split-digest regeneration, primary/challenge counts, sparse conduction analysis, single-class subject handling, context-precedence checks. |
| Outputs | Benchmark V1, split SHA, metrics protocol, challenge evidence policy, sealed test partition. |
| Exit gate | No change to test subjects/labels/window geometry/primary metric because of model results. |

Do not forget: Conduction challenge has only four subjects overall and is exploratory/descriptive; do not headline it.

# 9. Phase 3B-1 - Classical Global Baselines [RUNNING]

| Objective | Quantify how much of the task can already be solved with simple global non-personalized models. |
| --- | --- |
| Why it exists | The later CardioSentinel architecture must beat or improve upon credible simple baselines; otherwise advanced components may be unnecessary. |
| Technical process | B0 constant unsampled train prior; B1 signal_v1 logistic regression; B2 combined_v1 signal+morphology logistic regression; B3 combined_v1 HistGradientBoosting. Training uses all positives plus deterministic subject-aware max 3:1 negatives for B1-B3. Validation threshold maximizes F1 with fixed tie-break rule. |
| Experiments / checks | Validation AUPRC/AUROC/F1/sensitivity/PPV; subject-macro metrics; rate/axis challenge FPR; positive-context sensitivity; provenance SHA and lock checks. Only after all locks are frozen: one sealed-test evaluation per lock. |
| Outputs | Classical baseline table, frozen model artifacts, thresholds, experiment locks and sealed-test evidence. |
| Exit gate | B0-B3 technically sane, provenance-reviewed, immutable, then test evaluated exactly once. |

Do not forget: Do not interpret B0's 100% sensitivity/0% specificity as useful performance; it is a degenerate no-information reference.

## 9.1 B0 sanity result already observed

| Experiment | B0_constant_prior_v1 |
| --- | --- |
| Validation AUPRC | 0.04563860923365204 (equal to validation prevalence, as expected) |
| Validation AUROC | 0.5 |
| Validation threshold | 0.04367094778454366 (equal to unsampled training primary prevalence) |
| Behavior | All validation windows classify positive at the selected threshold; sensitivity 1.0, specificity 0.0. |
| Experiment lock Git SHA | 301d4bd6ca556a50f296813af0f1d326ac88c982 |

Current provenance note: A later read-only audit commit 9c8ac4697b934ff0569b07704f6d34eb053d7c9c was accidentally pushed while B1-B3 were running. It changes README + audit script + audit tests only, not scientific/model behavior. After B1-B3 complete, record each lock's Git SHA and decide whether a clean common-SHA refit is worth doing before sealed test evaluation.

# 10. Phase 3B-2 - Compact Raw-Waveform Neural Baseline [NEXT]

| Objective | Build a strong modern global neural comparator before adding personalization. |
| --- | --- |
| Why it exists | A final advanced system compared only with logistic regression would invite the criticism that any compact neural network could explain the gain. |
| Technical process | Train compact causal 1D time-series encoders directly on the frozen waveform geometry. Candidate backbone families are CNN/TCN, CNN+Tiny Transformer, and CNN+SSM. Use identical split, label semantics and validation-only architecture selection. |
| Experiments / checks | Compare validation AUPRC first, then parameter count, model size, latency, peak memory, training stability, challenge FPR, and later episode behavior. Multiple fixed seeds where feasible. |
| Outputs | B4 global neural model and an architecture-selection table. |
| Exit gate | Select a Pareto-efficient encoder and freeze it before patient adaptation. |

Do not forget: Do not choose the largest model simply because its AUPRC is numerically highest by a tiny amount.

## 10.1 Neural architecture candidates

| Candidate | Design | Scientific question | Selection logic |
| --- | --- | --- | --- |
| B4-A CNN/TCN | Depthwise/separable 1D convolution + dilated residual temporal blocks + pooling | How strong is an efficient local-temporal neural baseline? | Required reference. |
| B4-B CNN+Transformer | CNN morphology stem -> beat/patch tokens -> lightweight self-attention -> pooling | Does intra-window attention add useful context beyond CNN? | Keep only if gain justifies parameters/latency. |
| B4-C CNN+SSM | CNN morphology stem -> lightweight state-space temporal blocks | Can an SSM provide better performance/efficiency than short-context attention? | High-value candidate. |
| B4-D Hybrid | CNN + tiny Transformer per window + longitudinal SSM over window embeddings | Do short-context attention and long-context state modeling add distinct value? | Preferred advanced experiment if schedule permits. |

## 10.2 Architecture selection rule

Pareto rule: Choose the smallest/fastest architecture that is statistically competitive on validation and does not create a major challenge-robustness penalty. A 0.001-0.003 AUPRC increase is not automatically worth doubling parameters or latency. The paper should explain the performance-resource trade-off.

# 11. Phase 4 - Physiology-Guided Representation Learning [PLANNED]

| Objective | Make the learned representation sensitive to physiologically meaningful morphology rather than only generic waveform correlations. |
| --- | --- |
| Why it exists | This gives CardioSentinel an inductive bias aligned with the monitoring task and supports later patient-memory and explanation layers. |
| Technical process | Fuse neural embedding with explicit waveform-derived physiology descriptors. Later, if a validated delineation module is available, add ST level relative to PQ, ST slope, T-wave area/polarity, QRS width/morphology, RR statistics, beat-template correlation and cross-lead agreement. |
| Experiments / checks | Global neural vs +physiology fusion; feature-group ablations; challenge FPR; embedding visualization only as descriptive support, not proof. |
| Outputs | Physiology-aware representation and quantified incremental gain or robustness. |
| Exit gate | Retain physiology fusion only if it improves discrimination, robustness, interpretability, or personalization stability. |

Do not forget: Current morphology_v1 features are R-aligned waveform proxies; do not relabel them as validated ST/J-point delineation.

## 11.1 Optional contrastive/prototype representation experiment

A high-value Tier 2 extension is to structure the embedding space explicitly so stable within-patient windows cluster while event-related deviations separate. Candidate losses include supervised contrastive loss, prototype loss, or triplet-style objectives combined with the primary classification objective.

L_total = L_classification + lambda_c * L_contrastive + lambda_p * L_physiology [+ lambda_kd * L_distillation later]

# 12. Phase 4B - Foundation-Model Teacher and Knowledge Distillation [CONDITIONAL]

| Objective | Test whether a large pretrained ECG foundation model can transfer useful representation knowledge to the compact edge model. |
| --- | --- |
| Why it exists | This can create a credible foundation-to-edge contribution without deploying a 90M-parameter model on wearable hardware. |
| Technical process | Candidate teacher: ECG-FM. A generic 12-lead teacher/student setup may use PTB-XL for cross-lead distillation: teacher receives 12 leads; compact student receives two lead-identified channels with controlled lead dropout/amplitude perturbation. Distillation can match logits and latent embeddings, optionally with physiology consistency. |
| Experiments / checks | Student trained normally vs same student distilled; teacher vs student representation quality; downstream LTSTDB validation; edge size/latency retained. |
| Outputs | Evidence of whether foundation-model knowledge materially improves the compact student. |
| Exit gate | Keep distillation only if it produces a useful gain or robustness advantage. |

Do not forget: Lead mismatch is a major technical risk. Do not pretend a 12-lead teacher transfers cleanly to 2/3-lead ambulatory ECG without an explicit bridge.

## 12.1 Planned distillation objective

A candidate composite objective is:

L = L_cls + lambda1 * T^2 * KL(p_teacher ¦¦ p_student) + lambda2 * ¦¦ W e_student - e_teacher ¦¦^2 + lambda3 * L_phys + lambda4 * L_cal

# 13. Phase 5 - Patient-Adaptive Dual-Timescale Memory [CORE]

| Objective | Detect deviation from the patient's own stable physiological baseline rather than relying only on population-level abnormality. |
| --- | --- |
| Why it exists | Inter-patient morphology variation can create false alarms. A patient-specific baseline makes the task relative: what changed for this individual? |
| Technical process | Build z_t = [neural embedding; physiology features]. Maintain short-term and long-term normal prototypes with different update rates, plus shrinkage covariance or another stable distance model. Compute patient deviation using prototype distance / Mahalanobis-like score. |
| Experiments / checks | Global model vs personalized model; short-only vs long-only vs dual memory; subject-level false positives; sensitivity preservation; cold-start behavior. |
| Outputs | Evidence for RQ1: personalization changes the false-alarm/sensitivity trade-off. |
| Exit gate | Patient memory must reduce false alarms or improve operating trade-off without unacceptable sensitivity loss. |

Do not forget: Do not let patient identity itself become a leakage feature. Memory is updated online from past windows, not from test labels.

## 13.1 Dual-memory interpretation

| Memory | Role | Update behavior | Why both may be needed |
| --- | --- | --- | --- |
| Short-term prototype | Tracks recent stable physiology | Faster EMA / more responsive | Adapts to benign transient operating conditions. |
| Long-term prototype | Represents durable normal baseline | Slow EMA / conservative | Prevents temporary drift from redefining normality. |
| Rollback snapshots | Restores earlier normal state | Keep K prior prototypes | Protects against delayed discovery that a memory update occurred during an abnormal period. |

# 14. Phase 5B - Contamination-Safe Continual Adaptation [CORE]

| Objective | Prevent the personalization system from learning the developing event or severe artifact as normal. |
| --- | --- |
| Why it exists | Unsafe continual learning can erase the very anomaly the system is intended to detect. |
| Technical process | Update patient memory only under an explicit gate: adequate SQI, high normal probability, low uncertainty, no WATCH/EVENT refractory state, no axis-shift warning. Freeze memory in suspicious states. Preserve previous prototypes and allow rollback after later contradictory/cloud evidence. |
| Experiments / checks | Naive always-update vs gated update; gate without rollback vs gate+rollback; injected event contamination; noise and axis/rate stress conditions. |
| Outputs | Evidence for RQ2: safe adaptation limits baseline drift and preserves event detectability. |
| Exit gate | Gated adaptation outperforms or is materially safer than naive online updating. |

Do not forget: A sophisticated personalization module without a contamination experiment is incomplete.

# 15. Phase 6 - Calibration, Selective Prediction and Conformal Routing [CORE / HIGH VALUE]

| Objective | Quantify when the edge model should trust itself and when it should escalate. |
| --- | --- |
| Why it exists | In an edge/cloud system, uncertainty is not just a descriptive score; it controls resource use and safety. |
| Technical process | Calibrate on a subject-disjoint calibration/validation subset. Candidate uncertainty inputs: calibrated entropy, model variance if used, patient-prototype distance, signal quality, and disagreement across evidence streams. Build risk-coverage curves and a routing threshold selected only from validation. |
| Experiments / checks | Reliability, ECE, Brier score, selective risk, local coverage, error rate among accepted windows, cloud-escalation fraction. |
| Outputs | Calibrated uncertainty and an edge/cloud routing policy. |
| Exit gate | As local coverage is reduced, selective risk should improve in a stable and interpretable way. |

Do not forget: Do not call a confidence score 'uncertainty-aware' without calibration/selective evidence.

## 15.1 Conformal prediction experiment - strongly recommended

Conformal prediction is a Tier 2 experiment with unusually high conceptual value because it can turn ambiguity directly into an escalation policy.

{NORMAL} -> local normal decision {ISCHEMIC} -> high-confidence abnormal path / episode logic {NORMAL, ISCHEMIC} -> ambiguous -> cloud escalation

The exact conformal method must respect temporal/subject structure and must be calibrated without test leakage. If it is unstable under our non-exchangeable longitudinal setting, retain conventional calibrated selective prediction and report the limitation.

# 16. Phase 6B - Confounder-Aware Multi-Task Learning [TIER 2]

| Objective | Teach the neural encoder to distinguish ischemic ST patterns from rate-related, axis-related and quality-related changes. |
| --- | --- |
| Why it exists | The dataset contains explicit non-ischemic ST-related challenge states. Using training-only auxiliary supervision may reduce false alarms by learning what not to confuse with the target. |
| Technical process | Shared encoder with primary ischemia head and auxiliary rate/axis/quality heads. Conduction should be treated cautiously because the subject support is extremely sparse. Loss weighting is fixed using train/validation only. |
| Experiments / checks | Single-task vs multi-task; ischemic AUPRC/sensitivity; rate FPR; axis FPR; calibration and representation stability. |
| Outputs | Evidence whether confounder-aware auxiliary supervision improves target robustness. |
| Exit gate | Keep only if the primary task does not degrade materially and challenge FPR improves. |

Do not forget: Never allow challenge labels from validation/test to become training supervision.

# 17. Phase 7 - Longitudinal Temporal Modeling and Episode Reasoning [CORE]

| Objective | Move from isolated 10-second classification to continuous episode detection. |
| --- | --- |
| Why it exists | Transient ischemic ST events are sustained temporal phenomena. Window metrics alone do not describe alert quality. |
| Technical process | Two complementary layers are planned: a learned longitudinal SSM over successive window embeddings, and an interpretable state machine NORMAL -> WATCH -> EVENT -> RECOVERY with persistence/hysteresis. Memory freezes in WATCH/EVENT. Axis/conduction confounder evidence can suppress or escalate uncertain transitions. |
| Experiments / checks | Window-only vs SSM; window-only vs state machine; SSM+state machine; persistence threshold sensitivity; onset detection; false alarms/hour. |
| Outputs | Episode sensitivity, episode PPV, false alarms/hour, onset delay, temporal IoU and state traces. |
| Exit gate | Evidence for RQ4: temporal reasoning reduces isolated false alarms while preserving prompt event detection. |

Do not forget: Learned temporal state and operational state machine are not redundant: one models dynamics; the other controls alert behavior.

## 17.1 HMM/CRF temporal comparator - Tier 3

If time permits, include a simple probabilistic temporal comparator such as an HMM or CRF. This helps show whether gains come from any smoothing mechanism or from the chosen SSM/state design.

# 18. Phase 8 - Edge Deployment and Hardware-in-the-Loop [CORE]

| Objective | Demonstrate CardioSentinel as an intelligent physical system rather than an offline ML notebook. |
| --- | --- |
| Why it exists | TACTiCS alignment is much stronger if the paper proves that the intelligence can run under realistic edge resource and connectivity constraints. |
| Technical process | Initial edge target: Raspberry Pi 4B. Stream prerecorded ECG through an acquisition emulator; run causal preprocessing and compact model locally; route evidence via MQTT to a cloud-side teacher/service. Later add ESP32/acquisition front-end if feasible. Use INT8 quantization after the model is frozen. |
| Experiments / checks | Repeated latency runs (>=30), peak RAM, CPU, model size, INT8 size, bytes transmitted, local-decision coverage, packet loss, 60-300 s cloud outage, store-and-forward behavior and alert continuity. |
| Outputs | Edge systems table, latency distribution, network-savings result, outage behavior and deployment diagram. |
| Exit gate | Local inference is stable and routing produces measurable resource savings without breaking alert continuity. |

Do not forget: Do not invent energy numbers. Measure energy only if instrumentation is available.

## 18.1 Edge evidence packet

Compressed or bounded waveform snippet only when escalation is allowed.

Delineation/beat landmarks if available.

Physiology deltas relative to patient baseline.

Model logits/probabilities.

Patient-deviation score.

Uncertainty / conformal state.

Temporal state and persistence duration.

Source/model provenance identifiers.

# 19. Phase 9 - Ablation, Robustness and Secondary Evaluation [PLANNED]

| Objective | Prove which modules create value and how the system behaves when data are degraded or shifted. |
| --- | --- |
| Why it exists | A complex architecture is not a contribution unless component value is demonstrated and failure modes are characterized. |
| Technical process | Run controlled ablations; inject realistic signal perturbations; evaluate frozen challenge strata; optionally apply frozen models to provenance-aware EDB secondary cohort. |
| Experiments / checks | No physiology; no short memory; no long memory; no contamination gate; no rollback; no uncertainty routing; no temporal logic; no SSM. Perturb baseline wander, muscle artifact, electrode-motion transient, amplitude scaling, dropped samples, lead dropout. |
| Outputs | Ablation table, robustness curves, challenge FPR table, failure-case analysis, optional overlap-clean EDB result. |
| Exit gate | Every major claimed module has either measurable support or is removed/down-scoped in the paper. |

Do not forget: Negative results are scientifically useful. Do not hide a major component that failed to add value.

## 19.1 Recommended ablation ladder

| Step | System | Question answered |
| --- | --- | --- |
| A0 | Best global neural encoder | How strong is the non-personalized neural baseline? |
| A1 | + physiology fusion | Does explicit physiology add useful signal? |
| A2 | + patient dual-memory | Does personalization improve the operating trade-off? |
| A3 | + contamination gate | Can adaptation remain safe? |
| A4 | + rollback | Does recovery from contaminated updates matter? |
| A5 | + calibrated/conformal routing | Can ambiguous cases be selectively escalated? |
| A6 | + longitudinal SSM / temporal logic | Does temporal context reduce false alarms and improve episodes? |
| A7 | Full CardioSentinel | What is the complete system result? |

# 20. Phase 10 - Statistical Consolidation [PLANNED]

| Objective | Convert point estimates into defensible evidence and verify that the story survives subject-level variability. |
| --- | --- |
| Why it exists | Long ECG recordings generate many correlated windows, so treating windows as independent observations can overstate certainty. |
| Technical process | Use subject-level macro metrics and subject bootstrap confidence intervals. Where justified, use paired subject-level comparisons between frozen systems. Keep challenge evidence bounded by subject support. Review calibration and failure modes before writing claims. |
| Experiments / checks | 1000-subject bootstrap for primary metrics; paired comparisons; confidence intervals; sensitivity analyses; per-subject error distribution. |
| Outputs | Final quantitative evidence package for paper tables/figures. |
| Exit gate | Every central claim maps to an appropriate metric and uncertainty statement. |

Do not forget: Window count is huge but subject count is modest; never let millions of windows create false confidence.

# 21. Phase 11 - Paper Finalization [PLANNED]

| Objective | Compress the research into a rigorous 4-5 page IEEE-style TACTiCS paper. |
| --- | --- |
| Why it exists | The paper has too little space to narrate every development experiment, so only evidence that answers the research questions should occupy the main text. |
| Technical process | Finalize title and claims; update architecture figure; write method compactly; insert benchmark table, architecture-selection table/row, main ablation table, uncertainty/risk-coverage figure, episode/system metrics and limitations. Keep implementation details in repository artifacts. |
| Experiments / checks | Claim audit against repo; no TBD values; no unsupported external-validation or medical-device language; bibliography and originality check. |
| Outputs | Submission-ready manuscript with every numerical claim traceable to a frozen artifact. |
| Exit gate | No 'first' claim without literature support. No result is added from an untracked notebook or ad-hoc manual calculation. |

# 22. Phase 12 - Reproducibility Freeze and Submission [PLANNED]

| Objective | Freeze the exact code/data-identity/experiment state corresponding to the submitted paper. |
| --- | --- |
| Why it exists | Reviewers or future collaborators should be able to determine exactly how each result was generated. |
| Technical process | Merge reviewed code; create version tag/release; preserve experiment locks, result summaries, environment files and table-generation scripts; record paper-to-run mapping; archive final manuscript. |
| Experiments / checks | Final repo audit; all cited run IDs present; test-access audit; clean Git state; table/figure regeneration. |
| Outputs | One immutable submission snapshot. |
| Exit gate | Never rewrite history to make results look cleaner after submission. |

# 23. Advanced Experiment Tiers - What We Will Try and Why

This section is the 'do not forget' list of promising advanced techniques. The tiers are intentionally prioritized so optional experiments cannot crowd out the core contribution.

## 23.1 Tier 1 - Must Do

| Experiment | Reason | Decision criterion |
| --- | --- | --- |
| Compact CNN/TCN | Mandatory modern raw-waveform neural reference. | Establishes B4-A baseline. |
| CNN + tiny Transformer | Tests short-window attention beyond local convolution. | Keep only if performance/robustness gain justifies edge cost. |
| CNN + SSM | Tests efficient state-space temporal representation. | High-value competitor to Transformer. |
| Longitudinal SSM | Models progression across successive ECG windows. | Keep if episode/false-alarm behavior improves. |
| Patient dual-memory | Core patient-adaptive hypothesis. | Must improve subject-level operating trade-off. |
| Contamination-safe update | Makes continual adaptation scientifically credible. | Must prevent drift vs naive update. |
| Temporal state logic | Converts windows to episodes. | Must reduce isolated false alarms / improve episode metrics. |
| Calibration/selective routing | Operational edge/cloud intelligence. | Risk-coverage must be favorable. |
| Edge measurements | Physical-system proof. | Latency/memory/network/resilience evidence. |

## 23.2 Tier 2 - Very Desirable

| Experiment | Why it is attractive | How it fits the story |
| --- | --- | --- |
| Conformal prediction | More principled accept/ambiguous routing than arbitrary confidence thresholds. | Could become the cleanest edge/cloud escalation mechanism. |
| Confounder-aware multi-task learning | Uses rate/axis/quality training information to teach what not to confuse with ischemia. | Could reduce challenge false positives. |
| ECG-FM distillation | Foundation-to-edge transfer with compact deployment. | Strengthens modern representation story without putting FM on edge. |
| Contrastive/prototype representation learning | Structures embedding geometry for patient memory and deviation detection. | Could make personalization more stable and interpretable. |

## 23.3 Tier 3 - Only If Ahead of Schedule

| Experiment | Potential value | Why it is optional |
| --- | --- | --- |
| Full CNN + Transformer + SSM hybrid | Combines local, short-context and long-context modeling. | May add complexity without meaningful incremental value. |
| Masked ECG self-supervised pretraining | Learns time-series structure without task labels. | Training cost and schedule risk; FM distillation may already provide representation transfer. |
| HMM/CRF temporal comparator | Strong simple sequence baseline. | Useful but secondary if episode pipeline is already crowded. |
| Provenance-aware EDB secondary evaluation | Cross-cohort transfer evidence. | Requires careful harmonization and cannot be overclaimed as fully independent. |

## 23.4 Experiments intentionally deprioritized

| Technique | Reason not to prioritize |
| --- | --- |
| Spectrogram / image ViT | Raw time series is the natural input and ST morphology can be obscured by representation conversion. |
| Generic LLM ECG classifier | Weak scientific and safety justification; LLM is better used after structured detection. |
| Diffusion model | Does not directly answer the core detection/personalization/routing questions. |
| GNN over leads | Only 2/3 ambulatory channels make a lead-graph architecture difficult to justify. |
| Huge mixture-of-experts | Poor fit for constrained edge inference and limited scientific return for the deadline. |

# 24. Research Questions and Evidence Mapping

| RQ | Question | Primary experiment | Headline evidence |
| --- | --- | --- | --- |
| RQ1 | Does patient-specific memory reduce false alarms without sacrificing sensitivity? | Global neural vs dual-memory personalized model | Subject-level false alarms, sensitivity, PPV/AUPRC |
| RQ2 | Can continual personalization be made safe against contamination? | Naive update vs gated update vs gated+rollback | Drift, false alarms, event sensitivity under contamination |
| RQ3 | Can uncertainty reduce cloud dependence without increasing unsafe local decisions? | Calibrated/selective or conformal routing | Risk-coverage, local coverage, cloud fraction, bytes |
| RQ4 | Does longitudinal/episode reasoning improve monitoring quality? | Window-only vs SSM/state logic | Episode sensitivity, PPV, false alarms/hour, onset delay, temporal IoU |
| RQ5 | Can the selected model operate efficiently on edge hardware? | Pi/HIL deployment | Latency, RAM, CPU, model size, outage behavior |
| RQ6 | Does foundation-model knowledge improve the compact student? | Non-distilled vs ECG-FM-distilled student | AUPRC/robustness vs size/latency |
| RQ7 | Can confounder-aware supervision reduce false ST alarms? | Single-task vs multi-task | Rate/axis FPR with primary sensitivity preserved |

# 25. Metric Hierarchy

## 25.1 Window-level metrics

Primary: AUPRC.

Secondary: AUROC, F1, sensitivity, specificity, PPV, NPV, balanced accuracy, MCC.

Subject-macro versions where defined.

Subject bootstrap 95% confidence intervals for primary test evidence.

## 25.2 Challenge / confounder metrics

Rate-related confounder false-positive fraction: quantitative secondary evidence.

Axis-shift confounder false-positive fraction: quantitative secondary evidence.

Conduction challenge: exploratory/descriptive only because of extremely sparse subject support.

Positive ischemic windows carrying confounder context remain positive and are analyzed descriptively rather than removed.

## 25.3 Episode-level metrics - final system

Episode sensitivity.

Episode positive predictive value.

False alarms per hour.

Onset detection delay.

Temporal intersection-over-union / overlap.

Recovery / event-duration behavior where appropriate.

## 25.4 Calibration and routing metrics

Expected Calibration Error (ECE).

Brier score.

Reliability curves.

Selective risk / risk-coverage curve.

Local decision coverage.

Cloud escalation fraction.

Error rate among locally accepted decisions.

## 25.5 Edge-system metrics

Model parameters and serialized FP32/INT8 size.

Peak RAM.

Median / tail inference latency over repeated runs.

CPU utilization.

Network bytes transmitted per hour / per event.

Local-decision coverage.

Connectivity-loss behavior and alert continuity.

Energy only if directly measured with credible instrumentation.

# 26. What Results Go Into the Paper?

The paper should be transparent but selective. A 4-5 page manuscript cannot contain every development run. The correct principle is: report the experiments needed to establish the scientific claims, disclose important negative architecture results, and preserve the full ledger in the repository.

## 26.1 Results that should appear in the main paper

| Evidence block | Likely content | Purpose |
| --- | --- | --- |
| Baseline table | B0, B1, B2, B3, selected B4 global neural | Shows the scientific floor and strength of the neural comparator. |
| Architecture selection | CNN vs CNN+Transformer vs CNN+SSM; optionally hybrid | Explains why the deployed encoder was selected. |
| Core ablation | Global -> physiology -> patient memory -> safe adaptation -> routing -> temporal | Supports contribution claims. |
| Episode metrics | Sensitivity, PPV, false alarms/hour, onset delay | Demonstrates monitoring rather than only window classification. |
| Uncertainty / routing | Risk-coverage or local/cloud trade-off | Supports selective edge intelligence. |
| Edge system | Latency, RAM/model size, local coverage, bytes/outage behavior | Aligns with Intelligent Physical Systems. |
| Challenge robustness | Rate/axis FPR; conduction descriptive | Shows confounder awareness. |

## 26.2 Results that may be summarized rather than fully tabulated

Alternative architecture runs that are clearly dominated.

Failed spectrogram/image experiments if any are tried.

Minor hyperparameter diagnostics.

Development-only smoke tests.

Redundant models that do not change the research conclusion.

## 26.3 Negative results

A negative result should not be hidden if it explains a major architectural decision. For example, if CNN+Transformer+SSM adds negligible performance over CNN+SSM at twice the edge cost, the paper can state that the heavier hybrid was not retained because the improvement was not operationally meaningful.

## 26.4 What remains in the repository

cardiosentinel-runs/ B0/ B1/ B2/ B3/ B4_cnn/ B4_cnn_transformer/ B4_cnn_ssm/ B4_hybrid/ physiology/ contrastive/ personalized/ personalized_safe/ uncertainty/ conformal/ multitask/ temporal/ edge/ robustness/ ablations/ secondary_edb/ Every retained run: git SHA dirty state dataset/source identity split SHA feature corpus SHA where applicable config + seed environment model parameters validation threshold validation metrics test metrics only if authorized timing artifact hashes

# 27. Model Selection Decision Matrix

The chosen model is not simply the one with the highest validation AUPRC. CardioSentinel is an edge physical system, so selection must account for predictive quality and deployment cost.

| Criterion | Priority | How it is used |
| --- | --- | --- |
| Validation AUPRC | Highest | Primary discrimination criterion. |
| Subject-macro behavior | Highest | Reject models that win only through a few long records/subjects. |
| Challenge FPR | High | Prefer models that do not achieve AUPRC by overcalling non-ischemic ST changes. |
| Calibration / selective risk | High | Critical for routing decisions. |
| Parameter count / model size | High | Direct edge constraint. |
| Latency / peak RAM | High | Direct physical-system constraint. |
| Episode false alarms/hour | Highest later | Becomes more important than window F1 for the final system. |
| Training complexity | Medium | Matters for schedule/reproducibility but not a clinical operating metric. |
| Novelty / trendiness | Low | Never overrides evidence. |

# 28. Execution Schedule and Dependency Logic

| Window | Workstream | Dependency | Deliverable |
| --- | --- | --- | --- |
| 6-7 Aug | Repo/data/benchmark foundations | None | Phases 0-3A complete |
| 8-11 Aug | Feature corpus + classical baselines | Frozen benchmark | B0-B3 validation/test evidence |
| 12-15 Aug | Raw neural architecture selection | Baseline gate | CNN/Transformer/SSM comparison and B4 |
| 15-19 Aug | Core personalization + safe adaptation | Selected B4 encoder | Dual-memory and contamination ablations |
| 19-22 Aug | Uncertainty/conformal + temporal reasoning | Personalized encoder | Risk-coverage and episode metrics |
| 22-25 Aug | FM distillation / multi-task / contrastive as feasible | Core evidence stable | Tier 2 additions only if valuable |
| 24-26 Aug | Edge/HIL + quantization | Frozen selected system | Latency/RAM/network/outage results |
| 26-28 Aug | Ablations/robustness/statistics | Full system | Final evidence package |
| 29-30 Aug | Paper compression + claim audit | Final evidence | 4-5 page submission draft |
| 31 Aug | Freeze and submit | All gates closed | Submission snapshot |

Schedule rule: Tier 2/Tier 3 experiments must never delay personalization, uncertainty, temporal reasoning, or edge validation. Those are the core CardioSentinel contribution.

# 29. Current Execution Snapshot - 7 August 2026

| Current branch | research/phase-3b-classical-baselines |
| --- | --- |
| Latest pushed branch commit | 9c8ac4697b934ff0569b07704f6d34eb053d7c9c - Phase 3B: preserve corpus integrity audit |
| Feature generation commit | 4b20a284aac91155bbeefc134fd5fb448028fa8a - verified LTSTDB unit aliases |
| Feature corpus | f18785d520828cb171482926922346dda824c8868ed4b7f9be45897cd71d6eb5 |
| B0 state | Validation completed and mathematically sane. |
| B0 lock Git SHA | 301d4bd6ca556a50f296813af0f1d326ac88c982 |
| B1/B2/B3 | Running sequentially / awaiting completion at the time this handbook was created. |
| Test partition | Still sealed; do not evaluate until all B0-B3 validation locks and SHA provenance have been reviewed. |

## 29.1 Immediate next actions after B1-B3 finish

1. Collect RESULTS_SUMMARY.json from B0, B1, B2 and B3.

2. Record Git SHA, corpus SHA and experiment-lock SHA for each run.

3. Check whether the accidental read-only audit commit caused mixed fit Git SHAs.

4. Review validation AUPRC/AUROC, subject-macro behavior, thresholds, train sampling counts, challenge FPR and any warnings.

5. Do not modify model parameters based on test because test has not been opened.

6. If mixed SHAs create an unnecessarily messy reproducibility story, decide whether to refit under one clean SHA before test. Do not rerun automatically.

7. Once all four locks are accepted, evaluate the sealed test exactly once for each lock.

8. Build the first real baseline table.

9. Begin Phase 3B-2 neural architecture selection from the frozen benchmark.

# 30. Experiment Naming and Ledger

| Prefix | Meaning | Example |
| --- | --- | --- |
| B0-B3 | Classical baseline family | B2_morphology_logreg_v1 |
| B4-A | Compact CNN/TCN raw-waveform baseline | B4A_cnn_v1 |
| B4-B | CNN + Transformer | B4B_cnn_transformer_v1 |
| B4-C | CNN + SSM | B4C_cnn_ssm_v1 |
| B4-D | Short encoder + longitudinal SSM hybrid | B4D_hybrid_ssm_v1 |
| P1 | Physiology fusion | P1_phys_fusion_v1 |
| M1 | Patient dual-memory | M1_dual_memory_v1 |
| M2 | Contamination-safe memory | M2_safe_memory_v1 |
| U1 | Calibration/selective routing | U1_selective_v1 |
| U2 | Conformal routing | U2_conformal_v1 |
| T1 | Temporal episode reasoning | T1_state_machine_v1 |
| T2 | Longitudinal SSM + episode logic | T2_ssm_episode_v1 |
| KD1 | Foundation-model distillation | KD1_ecgfm_student_v1 |
| MT1 | Confounder-aware multi-task | MT1_rate_axis_quality_v1 |
| C1 | Contrastive/prototype representation | C1_supcon_v1 |
| E1 | Edge deployment/quantization | E1_pi4_int8_v1 |

## 30.1 Required run metadata

Experiment ID and model family.

Git SHA + dirty state.

Dataset/source identity and checksums.

Split SHA and sealed-test state.

Feature schema / waveform contract.

Model parameters and hyperparameters.

Random seed(s).

Training/calibration/threshold-selection partitions.

Environment/library versions.

Training and inference timing.

Artifact hashes.

Validation metrics.

Test metrics only after authorized sealed evaluation.

# 31. Research Risk Register

| Risk | Why it matters | Mitigation / decision |
| --- | --- | --- |
| Classical/neural baseline is unexpectedly strong | Could reduce apparent novelty of later architecture. | Good science: focus contribution on personalization, selective routing, episodes and physical-system evidence rather than raw classifier accuracy. |
| CNN+Transformer does not beat CNN | Attention may not add useful value for 10 s windows. | Drop it or use SSM; report architecture selection honestly. |
| SSM adds no value | Long-context dynamics may be captured by simpler temporal logic. | Keep state machine and patient memory; do not force SSM into final architecture. |
| FM lead mismatch | 12-lead pretrained models may not transfer cleanly to 2/3-lead ambulatory data. | Use explicit cross-lead distillation or make FM optional. |
| Personalization contaminates normal memory | Could suppress true events. | Hard update gate + freeze + rollback + contamination ablation. |
| Calibration poor under shift | Routing becomes unsafe/unreliable. | Use selective/conformal diagnostics and default uncertain cases to cloud/human review. |
| Conformal assumptions weak longitudinally | Coverage guarantee may not hold under non-exchangeable streams. | Use it as an experiment, report limitations, fall back to calibrated selective risk if needed. |
| Too many experiments for deadline | Core system could remain incomplete. | Tier discipline: finish core before Tier 2/3. |
| Paper page limit | Cannot report full ledger. | Main paper contains claim-bearing experiments; repository preserves all runs. |
| EDB overlap | Could invalidate external-validation wording. | Use provenance-clean exclusions and conservative language. |
| Huge window count inflates confidence | Windows are correlated within subjects. | Use subject-level metrics/bootstrap. |
| Hardware measurements unavailable | Weak Intelligent Physical Systems story. | Prioritize Pi4 latency/RAM/network/outage measurements over optional ML experiments. |

# 32. Claim Language Guide

| Avoid | Prefer |
| --- | --- |
| Diagnoses myocardial ischemia | Detects transient ECG episodes exhibiting ischemic ST-T characteristics / suspected ischemic ST change. |
| Clinically validated | Validated on public annotated ECG datasets under the stated benchmark protocol. |
| First ever system | We target a gap combining patient-adaptive memory, uncertainty-aware selective inference, temporal episode reasoning, and edge/cloud execution. |
| AI confidence | Calibrated probability / selective risk / conformal prediction set, depending on the implemented method. |
| External validation on EDB | Secondary provenance-aware EDB evaluation with known overlap exclusions. |
| 100% morphology validity | 3,164,305 / 3,164,370 windows satisfy the frozen morphology_v1 implementation criterion. |
| Mamba is more efficient | The SSM candidate is evaluated for performance-resource trade-off; deployment efficiency is reported only from our measurements. |

# 33. One-Page Memory Capsule

If only one page is read later: CardioSentinel is not a CNN project and not an LLM project. It is a patient-adaptive intelligent physical monitoring system. The research ladder is: frozen benchmark -> simple baselines -> compact raw neural encoder -> physiology -> patient dual-memory -> contamination-safe adaptation -> calibrated/selective or conformal uncertainty -> longitudinal/episode reasoning -> selective edge/cloud execution -> hardware evidence. CNN handles local morphology; a tiny Transformer may model short-window relationships; an SSM is especially valuable for long-range window-to-window state; a foundation ECG model may act as a teacher; an LLM/SLM is optional for explanation only. Every advanced component must survive an ablation or architecture-selection experiment.

## 33.1 The preferred final technical story

Large pretrained ECG teacher (optional, cloud/training) ¦ distillation v compact edge time-series encoder [CNN / Transformer / SSM selected by evidence] ¦ physiology-guided fusion ¦ patient short + long memory ¦ contamination-safe adaptation ¦ calibrated / conformal uncertainty ¦ longitudinal temporal reasoning ¦ NORMAL -> WATCH -> EVENT -> RECOVERY ¦ +-----------+------------+ ¦ ¦ v v local edge decision selective cloud ¦ structured evidence ¦ optional SLM/LLM human explanation

## 33.2 The core rule

Research rule: We are allowed to try advanced techniques. We are only allowed to claim the techniques that survive controlled experiments.

## 33.3 The next checkpoint

Finish B1/B2/B3. Audit their validation results and exact experiment SHAs. Keep test sealed until all four classical locks are accepted. Then perform one controlled sealed-test evaluation and use those results to open the neural architecture-selection phase.

# 34. Revision Log

| Version | Date | Change |
| --- | --- | --- |
| 1.0 | 7 Aug 2026 | Initial comprehensive research execution handbook capturing phases, architecture candidates, experiment tiers, paper strategy, frozen benchmark state, and current B0-B3 execution status. |